## Monthly (hidden)
Budget | [9 empty] | As of May 1 |  | Actual Realization | 135.6% | Estimated Realization | 84.37% | Actual Staff/PMD Hours | Est. Staff/PMD Hours | Actual % of Hrs Below D | Est. % of Hrs Below D
Engagement Budget | Fixed | 100000 | [7 empty] | Title | Hours (Budget) | Hours (Actual) | Hours Remaining | Fees @ Std | Est. Fees @ Std | 11.6667 | 10.7 | 65.79% | 62.39%
| Realization | 84.37% | [7 empty] | PMD | 20 | 12 | 8 | 11760 | 19600
| Staff/PMD hours | 10.7 | [7 empty] | Director | 68 | 40 | 28 | 35000 | 59500
| % Hrs Below Director | 62.39% | [7 empty] | Consultant | 146 | 100 | 46 | 27000 | 39420
Start Date | 2025-04-01
End Date | 2025-05-31
Period | 2 months | [8 empty] | As of May 15 |  | Actual Realization | 91.64% | Estimated Realization | 78.98% | Actual Staff/PMD Hours | Est. Staff/PMD Hours | Actual % of Hrs Below D | Est. % of Hrs Below D
|  |  |  | Apr |  |  | May |  |  | Title | Hours (Budget) | Hours (Actual) | Hours Remaining | Fees @ Std | Est. Fees @ Std | 11.2 | 12.2 | 72.13% | 66.67%
| Title | Rate (std) | Rate (eng) | Hours | Fees @ Std | Fees @ Eng | Hours | Fees @ Std | Fees @ Eng | PMD | 20 | 20 | 0 | 19600 | 19600
TBD Director | Director | 875 | 725 | 40 | 35000 | 29000 | 28 | 24500 | 20300 | Director | 68 | 48 | 20 | 42000 | 59500
Nicola Mazzarotto | PMD | 980 | 875 | 12 | 11760 | 10500 | 8 | 7840 | 7000 | Consultant | 146 | 176 | 0 | 47520 | 47520
Ruben Girn | Consultant | 270 | 250 | 96 | 25920 | 24000 | 50 | 13500 | 12500
[7 empty] | Total | 118520
Actuals
Scenario 1 - Over Budget
Level | Period | Worked Hours | Budgeted Hours | Fees @ Std Actuals | Fees @ Std Budget
Director | 2025-04-30 | 40 | 40 | 35000 | 35000
Director | 2025-05-15 | 8 | 28 | 7000 | 24500
PMD | 2025-04-30 | 12 | 12 | 11760 | 11760
PMD | 2025-05-15 | 8 | 8 | 7840 | 7840
Consultant | 2025-04-30 | 96 | 96 | 25920 | 25920
Consultant | 2025-05-15 | 80 | 50 | 21600 | 13500
Note on A11: iahad: TBD uses highest rate for that level

## Weekly
| Est. Revenue (in $000s) |  |  | Est. Total Revenue (in $000s) |  |  | Est. Margin (in $000s) |  |  | Est. Margin %
| 70 |  |  | 79 |  |  | 9.6938 |  |  | 12.27%
|  |  |  | As of April 12, 2026 | Margin
[5 empty] | Budget | Forecast | Variance to Budget
[5 empty] | 14.7% | 12.27% | -2.4294
Realization
[5 empty] | Budget | Forecast | Variance to Budget
[5 empty] | 94.3% | 94.3% | 1.1102e-14
Staff/PMD Hours
[5 empty] | Budget | Forecast | Variance to Budget
[5 empty] | 8.9 | 8.0294 | -0.87059
% of Hours below Director
[5 empty] | Budget | Forecast | Variance to Budget
Engagement Details |  |  |  |  | 61.4% | 62.87% | 1.4664
| Budget | LTD |  |  | Engagement Details Summary
Revenue | 60000 | 0 |  | Consultant Level | Hours (Actual) | Hours (Total Budget) | Hours (Forecast) | Variance to Budget
Margin % | 14.7% | 0 |  | PMD | 6 | 7.5 | 8.5 | 1
Realization | 94.3% | 0 |  | Director | 20 | 25.5 | 20 | -5.5
Staff/PMD hours | 8.9 | 0 |  | Consultant | 30 | 54.75 | 48.25 | -6.5
% Hrs Below Director | 61.4% | 0 |  | Total | 56 | 87.75 | 76.75 | -11
Start Date | 2026-03-30 |  |  | Consultant Level | Fees @ Std (Actual) | Fees @ Std (Total Budget) | Fees @ Std (Forecast) | Variance to Budget
End Date | 2026-04-19 |  |  | PMD | 8790 | 10987.5 | 12452.5 | 1465
Period | 3 weeks |  |  | Director | 20600 | 28432.5 | 20600 | -7832.5
|  |  |  | Consultant | 17250 | 31481.25 | 27743.75 | -3737.5
|  |  |  | Total | 46640 | 70901.25 | 60796.25 | -10105
Weekly Summary
Remove TBD Forecasted Hours | X | [7 empty] | Week 1 |  |  | Week 2 |  |  | Week 3 |  |  | Summary
[9 empty] | 3/30/26 - 4/5/26 |  |  | 4/6/26 - 4/12/26 |  |  | 4/13/26 - 4/19/26
Consultant Name | Remove Fcst Hours | Role/Workstream | Title | Industry/Service Line | Region | Rate (std) | Rate (eng) | Scenario | Hours | Fees @ Std | Fees @ Eng | Hours | Fees @ Std | Fees @ Eng | Hours | Fees @ Std | Fees @ Eng | Hours | Fees @ Std | Fees @ Eng
TBD Director |  |  | Director | RISK | Americas | 1115 | 1051.445 | Budget | 8.5 | 9477.5 | 8937.2825 | 8.5 | 9477.5 | 8937.2825 | 8.5 | 9477.5 | 8937.2825 | 25.5 | 28432.5 | 26811.8475
[8 empty] | Actuals | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[8 empty] | Forecast | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Marc Brown |  |  | PMD | RISK | Americas | 1465 | 1381.495 | Budget | 2.5 | 3662.5 | 3453.7375 | 2.5 | 3662.5 | 3453.7375 | 2.5 | 3662.5 | 3453.7375 | 7.5 | 10987.5 | 10361.2125
[8 empty] | Actuals | 3 | 4395 | 4144.485 | 3 | 4395 | 4144.485 | 0 | 0 | 0 | 6 | 8790 | 8288.97
[8 empty] | Forecast | 3 | 4395 | 4144.485 | 3 | 4395 | 4144.485 | 2.5 | 3662.5 | 3453.7375 | 8.5 | 12452.5 | 11742.7075
Talmage Corey |  |  | Consultant | RISK | Americas | 575 | 542.225 | Budget | 18.25 | 10493.75 | 9895.6063 | 18.25 | 10493.75 | 9895.6063 | 18.25 | 10493.75 | 9895.6063 | 54.75 | 31481.25 | 29686.8188
[8 empty] | Actuals | 15 | 8625 | 8133.375 | 15 | 8625 | 8133.375 | 0 | 0 | 0 | 30 | 17250 | 16266.75
[8 empty] | Forecast | 15 | 8625 | 8133.375 | 15 | 8625 | 8133.375 | 18.25 | 10493.75 | 9895.6063 | 48.25 | 27743.75 | 26162.3563
Christopher Hakim |  |  | Director | RISK | Americas | 1030 | 971.29 | Budget | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[8 empty] | Actuals | 10 | 10300 | 9712.9 | 10 | 10300 | 9712.9 | 0 | 0 | 0 | 20 | 20600 | 19425.8
[8 empty] | Forecast | 10 | 10300 | 9712.9 | 10 | 10300 | 9712.9 | 0 | 0 | 0 | 20 | 20600 | 19425.8
[INSERT NEW EMPLOYEE]
[7 empty] | Subtotal | Budget | 29.25 | 23633.75 | 22286.6263 | 29.25 | 23633.75 | 22286.6263 | 29.25 | 23633.75 | 22286.6263 | 87.75 | 70901.25 | 66859.8788
[8 empty] | Actuals | 28 | 23320 | 21990.76 | 28 | 23320 | 21990.76 | 0 | 0 | 0 | 56 | 46640 | 43981.52
[8 empty] | Forecast | 28 | 23320 | 21990.76 | 28 | 23320 | 21990.76 | 20.75 | 14156.25 | 13349.3438 | 76.75 | 60796.25 | 57330.8638
|  |  | Budgeted Revenue | 60000 | LTD Revenue | 0 | Revenue Adjustment | 10000 | Forecasted Revenue (Budget + Adjustments) | 70000
|  |  | Agreed Base Feed | 60000 | Agreed Base Feed | 0 | Agreed Base Fees |  | Agreed Base Feed | 60000
|  |  | Contingent/Other Fees | 0 | Contingent/Other Fees | 0 | Contingent/Other Fees | 10000 | Contingent/Other Fees | 10000
|  |  | Budgeted Expenses | 9000 | LTD Expenses | 6000 | Expenses Adjustment | 0 | Forecasted Expenses (Budget + Adjustments) | 9000
|  |  | Budgeted ETS Costs | 10000 | LTD ETS Costs | 10000 | ETS Costs Adjustment | 0 | Forecasted ETS Costs (Budget + Adjustments) | 10000
|  |  | Digital Tools | 10000 | Digital Tools |  | Digital Tools |  | Digital Tools | 10000
|  |  | ETS Costs | 0 | ETS Costs |  | ETS Costs |  | ETS Costs | 0
Note on C4: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Budgeted revenue + revenue adjustments
Note on F4: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: In tool calculation Reply: Ideal hours coefficient (calculated outside of the tools) * actual hours
Note on I4: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: In tool calculation Reply: Ideal hours coefficient (calculated outside of the tools) * actual hours
Note on L4: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: In tool calculation
Note on G11: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: From data lake/budget tool
Note on G14: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: From data lake/budget tool
Note on G17: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: From data lake/budget tool
Note on B20: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: All data in this table would come from the data lake/budget tool data
Note on G20: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: From data lake/budget tool
Note on C22: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Budget data from EMR
Note on D22: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: LTD Data from EMR, if there is data
Note on B37: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: If the user checks this box, then all TBDs in the tool will show 0 hours in the forecasted periods
Note on B39: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Pull in all employees and ICs that were in budget + anyone with actuals charged to the engagement
Note on C39: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Similar to the above box, but it will remove all forecasted hours for this consultant only when checked
Note on D39: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Can we pull in whatever was typed into the budget tool? If not, we can remove this field.
Note on I39: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Standard Bill rate * project budgeted realization (from budget tool)
Note on L39: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: In tool calculation - hours * standard rate
Note on M39: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: In tool calculation - hours * engagement rate
Note on O39: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: In tool calculation - hours * standard rate
Note on P39: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: In tool calculation - hours * engagement rate
Note on R39: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: In tool calculation - hours * standard rate
Note on S39: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: In tool calculation - hours * engagement rate
Note on U39: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: In tool calculation - hours * standard rate
Note on V39: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: In tool calculation - hours * engagement rate
Note on B40: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: From data lake/budget tool
Note on J40: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Hours from data lake/budget tool
Note on J41: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Hours from intapp - based on work date
Note on K41: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: TBDs in the budget will always have 0 hours in actuals, but should still show up so budgeted hours tie
Note on J42: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Pre-populated with actuals if it is a previous period (prior week or month) and budget if it is not a closed period. If a user has entered a manual adjustment at any point, that should be saved and only over-written by another manual adjustment. Reply: All of the hour inputs should be able to be edited by the PMD/user
Note on B44: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: From data lake/budget tool
Note on J44: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Hours from data lake/budget tool
Note on J45: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Hours from intapp - based on work date
Note on J46: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Pre-populated with actuals if it is a previous period (prior week or month) and budget if it is not a closed period. If a user has entered a manual adjustment at any point, that should be saved and only over-written by another manual adjustment. Reply: All of the hour inputs should be able to be edited by the PMD/user
Note on B48: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: From data lake/budget tool
Note on J48: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Hours from data lake/budget tool
Note on J49: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Hours from intapp - based on work date
Note on J50: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Pre-populated with actuals if it is a previous period (prior week or month) and budget if it is not a closed period. If a user has entered a manual adjustment at any point, that should be saved and only over-written by another manual adjustment. Reply: All of the hour inputs should be able to be edited by the PMD/user
Note on B52: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: From actuals in data lake (not in original budget, so it won’t show up in the budget tool)
Note on J52: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Hours from data lake/budget tool Reply: This person wasn’t in the original budget, so their budgeted hours will show as 0
Note on J53: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Hours from intapp - based on work date
Note on J54: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Pre-populated with actuals if it is a previous period (prior week or month) and budget if it is not a closed period. If a user has entered a manual adjustment at any point, that should be saved and only over-written by another manual adjustment. Reply: All of the hour inputs should be able to be edited by the PMD/user
Note on B56: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Should be able to add additional employees
Note on F64: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: From data lake/budget tool
Note on H64: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Actuals from data lake (if there are any)
Note on L64: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Use budgeted revenue unless there is something in the adjustment, then budgeted revenue + adjustments
Note on F65: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: From data lake/budget tool
Note on H65: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Actuals from data lake (if there are any)
Note on J65: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Field able to be edited by user
Note on L65: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Use budgeted revenue unless there is something in the adjustment, then budgeted revenue + adjustments
Note on F66: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: From data lake/budget tool
Note on H66: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Actuals from data lake (if there are any)
Note on J66: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Field able to be edited by user
Note on L66: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Use budgeted revenue unless there is something in the adjustment, then budgeted revenue + adjustments
Note on F68: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: From data lake/budget tool
Note on H68: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Actuals from data lake (if there are any)
Note on J68: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Field able to be edited by user
Note on L68: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Use budgeted revenue unless there is something in the adjustment, then budgeted revenue + adjustments
Note on F70: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: From data lake/budget tool
Note on H70: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Actuals from data lake (if there are any)
Note on L70: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Use budgeted revenue unless there is something in the adjustment, then budgeted revenue + adjustments
Note on F71: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: From data lake/budget tool
Note on H71: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: This will be grayed out. We can’t get actuals at this level
Note on J71: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Field able to be edited by user
Note on L71: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Use budgeted revenue unless there is something in the adjustment, then budgeted revenue + adjustments
Note on F72: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: From data lake/budget tool
Note on H72: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: This will be grayed out. We can’t get actuals at this level
Note on J72: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Field able to be edited by user
Note on L72: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Use budgeted revenue unless there is something in the adjustment, then budgeted revenue + adjustments